## Project Timeline
Project | Phase A | Phase F | Meeting | Semi-Weekly Meeting | Project Manager | Milestone | Notes | Hours
(I) Evaluation Project | Initiation | Initialisation | 1 | Jan. 5 | Royce |  |  | 5.5
Team work hours: 462 | Initiation | Initialisation | 2 | Jan. 7 | Royce |  |  | 5.5
| Planning | Pre-Study | 3 | Jan. 12 | Scott |  |  | 5.5
| Plan/Execute | Concept | 4 | Jan. 14 | Scott | Criteria for Broad |  | 5.5
| Plan/Execute |  | 5 | Jan. 19 | Adam | Easy broad done |  | 5.5
| Plan/Execute |  | 6 | Jan. 21 | Adam | End of broad; Deep criteria |  | 5.5
| Plan/Execute |  | 7 | Jan. 26 | Scott | Deep start |  | 5.5
| Plan/Execute |  | 8 | Jan. 28 | Scott |  |  | 5.5
| Plan/Execute |  | 9 | Feb. 2 | Adam |  |  | 5.5
| Plan/Execute |  | 10 | Feb. 4 | Adam |  |  | 5.5
| Execute |  | 11 | Feb. 9 | Scott |  |  | 5.5
| Execute |  | 12 | Feb. 11 | Scott |  |  | 5.5
|  |  | 13 | Feb. 16 | NO MEETING (due to Presidents Day) | End of Deep
|  |  | 14 | Feb. 18 | Royce | Write it up
| Article Due |  | 15 | Feb. 23 | Adam | Draft done |  | 5.5
|  |  | 16 | Feb. 25 | Adam | Revise article |  | 5.5
|  | Introduction | 17 | Mar. 1 | Final Changes / Celebration | Submission | BJET Special Issue
(II) Adaptation Project | Initiation |  | 18 | Mar. 3 | Royce |  |  | 5.5
Team work hours: 297 | Planning |  | 19 | Mar. 8 |  |  |  | 5.5
|  |  | 20 | Mar. 10 |  |  |  | 5.5
| Execution |  | 21 | Mar. 15 |  |  |  | 5.5
|  |  | 22 | Mar. 17 |  |  |  | 5.5
|  |  | 23 | Mar. 22 |  |  |  | 5.5
|  |  | 24 | Mar. 24 |  |  |  | 5.5
| Closeout |  | 25 | Mar. 29 |  |  |  | 5.5
|  |  | 26 | Mar. 31 | 3MT Presentations (?) |  |  | 5.5
|  |  | 27 | Apr. 5 | 3MT Presentations
|  |  | 28 | Apr. 7 | Celebration

## Gantt Chart
| Week 1 |  | Week 2 |  | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7 |  | Week 8 |  | Due
| 2016-01-05 | 2016-01-07 | 2016-01-12 | 2016-01-14 | 2016-01-19 | 2016-01-21 | 2016-01-26 | 2016-01-28 | 2016-02-02 | 2016-02-04 | 2016-02-09 | 2016-02-11 | 2016-02-16 | 2016-02-18 | 2016-02-23 | 2016-02-25 | 2016-03-01
Planning | bar: 2016-01-05 to 2016-01-21
-Initial Planning | bar: 2016-01-05 to 2016-01-07
-Broad Planning | bar: 2016-01-07 to 2016-01-12
-Deep Planning | bar: 2016-01-12 to 2016-01-21
Evaluation | bar: 2016-01-14 to 2016-02-18
-Broad Evaluation | bar: 2016-01-14 to 2016-01-21
-Deep Evaluation | bar: 2016-01-26 to 2016-02-18
Writing
-Literature Review | bar: 2016-01-05 to 2016-01-07
-Methods | bar: 2016-01-12 to 2016-01-28
-Results | 2016-02-18: Draft
-Revisions | bar: 2016-02-23 to 2016-02-25
Peer Review | bar: 2016-02-23 to 2016-02-25
Submit to BJET | bar: 2016-03-01

## Resources
Codename | Location | ID | Resource Name | Author | Copyright Type | Group Folder
Antelope | http://pm4id.org/ | PM4ID | Project Management for Instructional Designers | Amado et al. | Open | No (retrievable)
Badger | http://opentextbc.ca/projectmanagement/ | UBCPM | Project Management | Watt | Open | Yes
Fox | HBLL Online | PMH | Project Management Handbook | Kuster et al. | Restricted | Yes
Grasshopper | HBLL Online | UPM | Understanding Project Management | Straw | Restricted | Yes (partial)
Hummingbird | HBLL Online | RPM | Real Project Management | Taylor | Restricted | Yes (partial)
Jellyfish | HBLL Online | PM2 | Project Management 2.0 | Kerzner | Restricted | Yes
Kangaroo | HBLL Online | PMM | Project Management Maturity Model | Crawford | Restricted | Yes (partial)
Mallard | HBLL Online | ISPM | Information Systems Project Management | Olson | Restricted | Yes